## SPERT® Normal - CFD Charts
Statistical PERT® (SPERT®) Normal Edition Cumulative Flow Diagram (CFD) Stacked Area Charts
Day | Date | Product Backlog | Design | Developing | PO Review | Done | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V
Need more process steps? Unhide columns H-V. Rename process steps to fit your workflow.
Hide any columns you don't use to remove them from the CFD charts below.
You may overwrite Row 6's data, but DO NOT DELETE the data in Row 6 or else Excel formula errors will occur
1 | 2024-10-04 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2024-10-05 | 4 | 0 | 0 | 0 | 0
3 | 2024-10-06 | 3 | 1 | 0 | 0 | 0
4 | 2024-10-07 | 3 | 1 | 0 | 0 | 0
5 | 2024-10-08 | 2 | 2 | 0 | 0 | 0
6 | 2024-10-09 | 6 | 2 | 0 | 0 | 0
7 | 2024-10-10 | 4 | 3 | 1 | 0 | 0
8 | 2024-10-11 | 2 | 4 | 2 | 0 | 0
9 | 2024-10-12 | 2 | 4 | 1 | 1 | 0
10 | 2024-10-13 | 0 | 4 | 3 | 1 | 0
11 | 2024-10-14 | 0 | 2 | 3 | 2 | 1
12 | 2024-10-15 | 19 | 0 | 3 | 3 | 2
13 | 2024-10-16 | 19 | 0 | 3 | 0 | 5
14 | 2024-10-17 | 19 | 0 | 1 | 2 | 5
15 | 2024-10-18 | 19 | 0 | 0 | 1 | 7
16 | 2024-10-19 | 21 | 4 | 0 | 0 | 8
17 | 2024-10-20 | 25 | 8 | 2 | 0 | 8
18 | 2024-10-21 | 25 | 8 | 2 | 0 | 8
19 | 2024-10-22 | 25 | 7 | 3 | 0 | 8
20 | 2024-10-23 | 25 | 5 | 5 | 0 | 8
21 | 2024-10-24 | 25 | 5 | 5 | 0 | 8
22 | 2024-10-25 | 36 | 6 | 5 | 5 | 8
23 | 2024-10-26 | 28 | 4 | 6 | 1 | 14
24 | 2024-10-27 | 28 | 2 | 6 | 2 | 15
25 | 2024-10-28 | 25 | 4 | 3 | 4 | 17
26 | 2024-10-29 | 20 | 5 | 7 | 4 | 17
27 | 2024-10-30 | 20 | 2 | 6 | 8 | 17
28 | 2024-10-31 | 19 | 1 | 5 | 4 | 23
29 | 2024-11-01 | 35 | 4 | 3 | 3 | 27
30 | 2024-11-02 | 35 | 4 | 3 | 0 | 30
31 | 2024-11-03 | 34 | 4 | 4 | 0 | 30
32 | 2024-11-04 | 34 | 4 | 2 | 2 | 30
33 | 2024-11-05 | 30 | 6 | 4 | 2 | 30
34 | 2024-11-06 | 30 | 6 | 2 | 4 | 30
35 | 2024-11-07 | 28 | 2 | 2 | 2 | 34
36 | 2024-11-08 | 41 | 1 | 3 | 2 | 34
37 | 2024-11-09 | 41 | 0 | 3 | 3 | 34
38 | 2024-11-10 | 40 | 1 | 3 | 2 | 35
39 | 2024-11-11 | 40 | 1 | 2 | 3 | 35
40 | 2024-11-12 | 40 | 1 | 2 | 0 | 38
41 | 2024-11-13 | 40 | 0 | 2 | 0 | 38
42 | 2024-11-14 | 39 | 1 | 1 | 1 | 38
43 | 2024-11-15 | 36 | 3 | 2 | 1 | 38
44 | 2024-11-16 | 36 | 2 | 3 | 0 | 39
45 | 2024-11-17 | 36 | 1 | 3 | 1 | 39
46 | 2024-11-18 | 36 | 0 | 3 | 1 | 40
47 | 2024-11-19 | 33 | 3 | 1 | 3 | 40
48 | 2024-11-20 | 33 | 2 | 2 | 2 | 41
49 | 2024-11-21 | 30 | 3 | 3 | 1 | 43
50 | 2024-11-22 | 30 | 1 | 2 | 3 | 44
51 | 2024-11-23 | 27 | 3 | 2 | 1 | 47
52 | 2024-11-24 | 27 | 2 | 2 | 2 | 47
53 | 2024-11-25 | 27 | 0 | 3 | 1 | 49
54 | 2024-11-26 | 27 | 0 | 3 | 1 | 49
55 | 2024-11-27 | 27 | 0 | 2 | 1 | 50
56 | 2024-11-28 | 27 | 0 | 1 | 2 | 50
57 | 2024-11-29 | 27 | 0 | 1 | 0 | 52
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300 | [21 empty] | © 2015-2022, William W. Davis, MSPM, PMP
Need more rows? Unhide rows 51-305.
For the WIP Only chart above, the example "Done" column is de-selected. Adjust this chart by choosing
only the true work-in-progress (WIP) process steps after you customize this worksheet to your workflow.
Then, right-click on the chart and choose "Select data…" and de-select your "Done" column.
#REF!
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Click for help
Note on B2: Enter only the work days for your team. You can exclude holidays, weekends and other non-work days so your CFD doesn't react to non-work days, making it easier to spot process issues.
Note on A5: The SPERT® CFD chart uses dynamic cell ranges to draw the Excel 2-D, stacked area chart that creates the CFD. These dynamic ranges require that at least some data exists in each cell range, or else Excel will throw an error. To avoid errors with dynamic cell ranges, there are default numbers pre-filled in Row 6 (Day 1). You may overwrite the default numbers in Row 6, but do not delete the data in Row 6.